## Schedule
Project Schedule
| Project Name: | Digital M
| Project Manager Name: | Nuha Bahaa
| Project Start Date: | March 5th, 2016
| Project Schedule Last Updated Date: | March 19th, 2016
ID | Task Name | Duration |  | Status | Expected Start | Actual Start | Expected Finish | Actual Finish | % Complete | Resource Names
0 | Project Schedule | 35 | days | Current | 2016-03-05 | 2016-03-06 | 2016-04-10 | NA | 85%
1 | Project Management Activities | 7 | days |  | 2016-03-05 | 2016-03-07 | 2016-03-11 | 2016-03-11 | 100%
2 | Complete Project Charter | 7 | days | done | 2016-03-05 | 2016-03-07 | 2016-03-11 | 2016-03-11 | 100%
3 | Complete Project Management Plan | 7 | days | done | 2016-03-05 | 2016-03-07 | 2016-03-11 | 2016-03-11 | 100%
4 | Conduct Monitoring & Controlling Activities | 7 | days | done | 2016-03-05 | 2016-03-07 | 2016-03-11 | 2016-03-11 | 100%
5 | Management Activities Completed
6 | Initiation/Planning | 7 | days | done | 2016-03-12 | 2016-03-12 | 2016-03-17 | 2016-03-17 | 100%
7 | CRS-SRS | 2 | days | done | 2016-03-12 | 2016-03-12 | 2016-03-14 | 2016-03-14 | 100%
8 | SIQ-RTM | 2 | days | done | 2016-03-15 | 2016-03-14 | 2016-03-17 | 2016-03-18 | 100%
9 | Test cases | 2 | days | done | 2016-03-19 | 2016-03-19 | 2016-03-22 | 2016-03-22 | 100%
10 | Initiation/Planning Activities Completed
11 | Requirements Analysis | 1 | days | done | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 100%
12 | Hardware burchasing | 1 | days | done | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 100%
13 | Requirements Analysis Completed
14 | Design | 4 | days | done | 2016-03-19 | 2016-03-19 | 2016-03-24 | 2016-03-24 | 100%
15 | Ultrasonic CDD | 2 | days | done | 2016-03-25 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 100% | fanni+kamal
16 | LCD CDD | 2 | days | done | 2016-03-25 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 100% | anas
17 | Buzzer CDD | 2 | days | done | 2016-03-25 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 100% | nuha
| HLD | 2 | days | done | 2016-03-19 | 2016-03-22 | 2016-03-19 | 2016-03-22 | 100% | mahmoud
18 | update the project schedule | 2 | days | done | 2016-03-22 | 2016-03-25 | 2016-03-30 | 2016-04-01 | 100% | Aya+Mahmoud
19 | Development | 15 | days | current | 2016-03-25 | 2016-03-25 | 2016-04-01 | 2016-04-01 | 100%
20 | Code ultrasonic development | 2 | days | done | 2016-03-25 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 100% | fanni+kamal
21 | Code LCD+ DIO development | 2 | days | done | 2016-03-25 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 100% | anas
22 | Code buzzer development | 2 | days | done | 2016-03-25 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 100% | aya
23 | update RTM with design | 5 | days | done | 2016-03-22 | 2016-03-26 | 2016-03-27 | 2016-03-31 | 100% | nuha
26 | Test Case | 3 | days | done | 2016-03-27 | 2016-03-28 | 2016-03-30 | 2016-03-31 | 100% | nuha
27 | Application development | 1 | day | in progress | 2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 80% | aya
28
29
30 | Development Completed
31 | Test | 4 | days | NA | 2016-04-02 | NA | 2016-04-05 | NA | 0%
32 | Complete Unit test | 1 | days | done | 2016-04-29 | 2016-04-29 | 2016-04-01 | 2016-04-01 | 80%
33 | Complete Function Test | 1 | days | NA | 2016-04-02 | NA | 2016-04-09 | NA | 0%
34 | Complete Integration Test | 1 | days | NA | 2016-04-02 | NA | 2016-04-09 | NA | 0%
37 | Complete User Acceptance Test | 1 | days | NA | 2016-04-02 | NA | 2016-04-09 | NA | 0%
38 | Test Completed
39 | Implementation | 2 | days | NA | 2016-04-06 | NA | 2016-04-07 | NA | 0%
40 | Complete Deployment | 1 | days | NA | 2016-04-06 | NA | 2016-04-06 | NA | 0%
41 | Complete Training | 1 | days | NA | 2016-04-06 | NA | 2016-04-06 | NA | 0%
42 | Complete Support | 1 | days | NA | 2016-04-07 | NA | 2016-04-07 | NA | 0%
43 | Development/Implementation Completed
44 | Operations & Maintenance | 2 | days | NA | 2016-04-08 | NA | 2016-04-08 | NA | 0%
45 | Complete Operations Activities | 1 | days | NA | 2016-04-08 | NA | 2016-04-08 | NA | 0%
46 | Complete Maintenance Activities | 1 | days | NA | 2016-04-08 | NA | 2016-04-08 | NA | 0%
47 | Operations & Maintenance Completed
48 | Project Completed |  |  |  | 2016-03-05 |  | 2016-04-10