## Sheet1
Risk | Category | Probability(1-5) | Impact(1-10) | Handling
some components aren't avaiable at the current time . | requirement risk | 2 | 3 | Avoid
demage of one of the component. | requirement risk | 4 | 8 | mitigate by buy extra componnets
requirements are poorly defines and further definition expends the scope of the project. | requirement risk | 3 | 6 | Accept
schedule aren't realistic . | schedule risk | 2 | 5 | accept
important task missing from the schedule . | schedule risk | 4 | 7 | accept
unfamiliar areas of the product take more time than expected to design and implemnet. | schedule risk |  |  | accept
Customer insists on new requirements. | customer risk | 3 | 4 | accept
Customer will not accept the software as delivered even though it meets all specifications. | customer risk | 2 | 7 | accept
Customer has expectations for development speed that developers cannot meet. | customer risk | 2 | 6 | mitigate by speeding up the proceses
Personnel need extra time to learn unfamiliar software tools, hardware and programming language. | human resource risk | 3 | 6 | accept
stuff are really busy in other projects. | human resource risk | 4 | 7 | mitigate by dedicating specific time for the project
Conflicts among team members result in poor communication, poor designs, interface errors and extra rework. | human resource risk | 3 | 7 | avoid
Personnel with critical skills needed for the project cannot be found. | human resource risk | 3 | 5 | avoid
some problems occur to the laptop which has the code | technical risk | 4 | 8 | mitigate by upload the code on github